## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

PROJECT NUMBER	56
PROJECT NAME	Lab-authoring-project
PROJECT MENTOR (sponsor)	lalit
TEAM MEMBERS	Aanshul Sadaria
	Krutam Hathi
	Shovan Swain

## Status
PROJECT NUMBER	56
PROJECT NAME	Lab-authoring-project
PROJECT MENTOR (sponsor)	Lalit

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 1 (August 14- August 20)
Fix meeting with client	Coordination	Shovan	0.2	0.2	Done		0	0
GIT Repository setup	Preparation	Aanshul	0.5	0.3	Done		0.2	66.6666666666666
Client meeting	Coordination	Krutam	0.5	0.8	Done	Make sure scoping questions are included	-0.3	37.5
Get account and configure website	Preparation	Aanshul	1.5	1.2	Done		0.3	25
Research existing technology	Preparation	Krutam	1	1.3	Done		-0.3	23.0769230769231
Project synopsis writeup	Documentation	Shovan	2	2.5	Done		-0.5	20
			1
Team Meeting	Coordination	Shovan	0.5	0.8	Done		-0.3	37.5
Status tracker	Documentation	Krutam	1	0.8	Done		0.2	25
Week 2 (August 21 - August 27)
Learn Drag and Drop	Preparation	Aanshul	4	4.5	Done	Refering websites can do.	-0.5	11.1111111111111
GIT Repo updated	Preparation	Shovan	1	1.5	Done		-0.5	33.3333333333333
Try to complete a lab	Preparation	Krutam	4	5	Ongoing	This is critical to project success	-1	20
Select images	Preparation	Aanshul	1.5	1	Done		0.5	50
Team Meeting	Coordination	Krutam	0.3	0.2	Done		0.1	50
Status tracker	Documentation	Shovan	0.5	0.5	Done		0	0

Week 3 (August 28 – September 3)
Client meeting	Coordination	Shovan	0.5	0.8	Done		-0.3	37.5
SVG images	Preparation	Krutam	1	0.7	Done		0.3	42.8571428571429
functions of euips	Preparation	Aanshul	1.5	1.5	Done		0	0
Week 4 (September 4-- September 11)
Client meeting	Coordination	Aanshul	0.5	0.5	Done		0	0
Phet Simulations	Preparation	Shovan	1.5	1.5	Done		0	0
Making a lab	Preparation	Krutam,aanshul	2	1	Ongoing		1	100
Status tracker	Documentation	Krutam	0.5	0.5	done		0	0
Requirements listing	Documentation	Shovan	0.6	0.8	done		-0.2	25

Week 5(September 12-September 19)
Client meeting	Coordination	Shovan	0.5	0.5	done		0	0
Concept part of lab	Preparation	Krutam	2	1.5	Ongoing		0.5	33.3333333333333
Experimental Part	Preparation	Shovan	2	1.8	Ongoing		0.2	11.1111111111111
Home page building	Preparation	Aanshul	2	2	Ongoing		0	0
Status tracker	Documentation	Krutam	0.8	0.6	done		0.2	33.3333333333333
Week 6(September 20-September 27)
Update doucuments	Documentation	Shovan	1	1	Done		0	0
Update doucuments	Documentation	Krutam	1	1	Done		0	0

Week 7(Sept 28-Oct 7)
Client meeting	Coordination	Shovan	0.5	0.5	done		0	0
Improv the UI	Preparation	Krutam	1.5	2	Ongoing		-0.5	25
Improv the experiment	Preparation	Shovan	2	2	Ongoing		0	0

Week 8(Oct 8-Oct 15)
Client meeting	Coordination	Shovan	0.5	0.5	done		0	0
Designing the comment box	Preparation	Aanshul	0.5	0.5	done		0	0
Improv the experiment	Preparation	Shovan	1	1	done		0	0
Improv the UI	Preparation	Krutam	0.5	0.5	done		0	0
Status tracker	Documentation	Krutam	0.5	0.5	done		0	0